## START HERE
Clinical Care Gap Explorer — Build Plan
You build it. This workbook tells you WHAT to build and HOW YOU'LL KNOW IT'S RIGHT — not how to write the code.
How to use this
1. Work the Task Tracker top to bottom | Tasks are ordered by dependency, not importance. Do not jump ahead — Day 3 will not work if Day 1's profiling was skipped.
2. Read 'Done when' before you start a task | That column is the acceptance test. If you can't demonstrate it, the task is not done, no matter how much code you wrote.
3. Use the 'Go find out' column, not me | It names the concept or flag to search for. Looking it up yourself is the part that becomes interview knowledge. Ask me only after you've tried and are stuck on a specific error.
4. Log every decision in the Decisions sheet | Two of them (the cohort definitions) are the most interview-relevant lines in the whole repo. If you can't defend the choice out loud, the project doesn't land.
5. Fill the Learning Log at the end of each day | Rate 1-5 how well you could explain each concept unprompted. Anything at 3 or below is a hole to close before you send the link to anyone.
Ground rules
Commit at the end of every day | A recruiter who opens your repo sees the commit history. Seven days of steady commits reads very differently from one commit called 'initial'.
Never commit the Synthea output | It is regenerable and large. Set up .gitignore in task 1.2, BEFORE you generate data. Removing it from history afterwards is painful.
Cut scope, never cut the day | PRD section 9 says this. If Day 5 runs long, drop a feature and move on. A finished 4-page app beats an unfinished 5-page one.
Never write 'HIPAA compliant' | ACCESS_CONTROL.md is emphatic. The phrase is 'models minimum-necessary access by clinical role.' One wrong word here costs you credibility with anyone who works in health tech.
Every number in the README is measured, not estimated | Row counts, catch rate, cohort size. If you didn't run the query, leave the blank in.
Which doc governs what
docs/PRD.md | Scope. The non-goals list is binding — check it any time you're tempted to add something.
docs/DATA_DICTIONARY.md | Table and column definitions. The cohort definition blanks live at the bottom.
docs/DATA_QUALITY_SPEC.md | The six injected defects, the six checks, and the three tables they produce.
docs/ACCESS_CONTROL.md | Role matrix and the language rules for talking about it publicly.
docs/README_TEMPLATE.md | The blanks you fill on Day 7. Read it on Day 1 so you know what you're collecting.
Sheet guide
Day Plan | The 7-day arc at a glance. One row per day. Read this first.
Task Tracker | Where you actually live. ~55 tasks with done-criteria. Filter by Day.
Decisions | Every judgment call the docs left open. Record your answer AND your reasoning.
DQ Matrix | Injected defects vs. checks. Catch rate calculates itself once you fill the counts.
Metrics | The numbers the README needs. Fill as you measure them.
Learning Log | The interview questions this project should make you able to answer.

## Day Plan
The 7-day arc
~3 hrs/day. 'Ship gate' is the one thing that must be true before you start the next day.
Day | Theme | What you build | Why this order | Ship gate — must be true before Day N+1 | Hrs
1 | Ground truth | Repo skeleton, Python env, Synthea generation, profiling the raw output, Bronze load into DuckDB. | Every downstream blank depends on what Synthea actually emits. You cannot define the cohort from a doc — only from the data. | Bronze tables exist in DuckDB, row counts match the CSVs, and you have written down the real diabetes SNOMED codes and the A1c LOINC code. | 3
2 | Break it on purpose | corrupt.py — inject the six defect classes into Bronze — and injected_defects.json recording every injected row. | You inject before you check, so the checks have something to find. And you log the injection so catch rate is a measurement, not a claim. | injected_defects.json exists, and its row count equals the number of rows you actually corrupted. | 3
3 | The validation layer | DQ1-DQ6, the quarantine / identity_review / remediation_log tables, and Silver. | This is the actual subject of the project. The care-gap query is easy; this is the part that makes it trustworthy. | For every table: bronze rows = silver rows + quarantined rows. No silent drops (FR2). Catch rate computed. | 3
4 | The answer | Lock both cohort definitions, build gold care_gap_a1c, wire the pipeline to one command. | Gold is only meaningful once Silver is trustworthy. Definitions get locked here because now you know what the data supports. | One command runs Synthea-to-Gold end to end (FR1), and you have hand-verified three patients against the raw CSVs. | 3
5 | Make it visible | Next.js app, synthetic-data banner, P1 Overview, P2 Pipeline & Data Quality. Deploy for the first time. | P2 before P3 — the data quality work is the differentiator, so it gets built while you still have energy. | A public URL exists and shows P1 and P2 with real numbers. Deploy on Day 5, not Day 7. | 3
6 | Access by role | P3 Patient Care: the cohort list, gap-by-age chart, PCT / Nurse / Physician filtering — server-side. | Needs Gold finished and the app shell working. The role matrix is where your PCT experience shows up. | With PCT selected, dev tools shows no A1c values in the network payload. If they're there, the demo argues against itself. | 3
7 | Ask it anything, then ship | P4 natural-language-to-SQL with SELECT-only enforcement, audit log, error sweep, README, deploy, Loom. | Last because it's the most cuttable. If a day ran long, this is the page that shrinks. | Five deliberately hostile questions return five clean sentences. No stack trace is reachable from any page. | 3

## Task Tracker
Task Tracker
Amber columns are yours to fill. 'Done when' is the acceptance test — if you can't demonstrate it, it isn't done.
ID | Day | Task | Why it matters | Done when | Go find out (search these) | Status | Your notes / blockers | Progress
1.1 | 1 | Run git init here and make a first commit containing only docs/. | This folder is not a git repo yet. Commit history is part of the portfolio — a reviewer reads it. | git log shows one commit and git status is clean. | git init, writing a good commit message | Done |  | Done
1.2 | 1 | Write .gitignore BEFORE generating any data. Exclude Synthea output, the DuckDB file, venv, node_modules. | Synthea emits hundreds of MB. Committing it once means it lives in your history forever, and the repo becomes unclonable. | After Day 1's data generation, git status still shows nothing to commit under data/. | gitignore templates Python + Node, git check-ignore -v | Done |  | Total | 70
1.3 | 1 | Create the folder skeleton: pipeline/, data/raw/, data/warehouse/, web/. | A flat repo of loose scripts reads as a homework assignment. Structure signals intent. | Folders exist and .gitkeep (or similar) keeps the empty ones tracked. | why empty dirs aren't tracked in git | Done |  | Complete
1.4 | 1 | Create a Python virtual environment and install duckdb and pandas into it. Freeze to requirements.txt. | The README promises a run command. It has to work on a machine that isn't yours. | A fresh shell can activate the venv, import duckdb, and requirements.txt is committed. | python -m venv, pip freeze, why not global pip install | Done |  | Blocked
1.5 | 1 | Get Synthea running. Confirm it executes before you try to generate anything real. | Getting the tool working and generating the right data are two separate problems. Don't debug them at the same time. | You can run Synthea and it prints usage/help without error. | Synthea GitHub releases, synthea-with-dependencies.jar, java -jar | Done
1.6 | 1 | Decide population size, state, and a fixed random seed. Record all three in the Decisions sheet. | A fixed seed means a reviewer re-running your pipeline gets the numbers in your README. Without it, your README is unverifiable. | The three values are written down, and re-running with the same seed produces identical row counts. | Synthea -p and -s flags, reproducibility in data pipelines | Done | V1.3 failed with -s alone (data grew 4-6% four weeks later). Fixed with -cs -r -e; regenerated 2026-09-20. Full command in DAY_1_DECISIONS.md D2.
1.7 | 1 | Generate the population with CSV export turned on. | Synthea defaults to FHIR JSON. You want flat CSVs — FHIR conformance is an explicit non-goal. | data/raw/ contains patients, encounters, conditions, observations and medications CSVs. | exporter.csv.export property, synthea.properties file, --exporter flags | Done
1.8 | 1 | PROFILE: count rows in each CSV. Record them in the Metrics sheet as your Bronze baseline. | Every later assertion (bronze = silver + quarantine) is measured against these numbers. | Metrics sheet has a row count per source file. | wc -l, DuckDB read_csv_auto, count(*) | Done | Row counts in Metrics 1-5. profile.py replaces the ad-hoc loop.
1.9 | 1 | PROFILE: find every distinct diabetes-related SNOMED code in conditions, and how many distinct patients carry each. | You cannot define 'diabetic patient' from a document. This query is what makes that definition defensible. | The codes and their patient counts are written into docs/DATA_DICTIONARY.md, replacing the placeholder text. | SNOMED CT browser, type 2 diabetes mellitus SNOMED code, GROUP BY | Done | 8 cohort codes; 73 patients have a complication but no T2DM code. See cohort.py.
1.10 | 1 | PROFILE: confirm the A1c LOINC code, its unit string, and the min / median / max of its values. | DQ3's plausible range (3.0-20.0%) has to match reality before you inject a 250 into it. If Synthea emits mmol/mol, the whole check changes. | You know the exact LOINC code you'll filter on and the real value distribution. | LOINC 4548-4, hemoglobin A1c units % vs mmol/mol, percentile in SQL | Done | Units are %, so DQ3 order of magnitude OK — but floor 3.0 flags 951 clean values.
1.11 | 1 | PROFILE: what fraction of diabetes condition rows have a resolved_date? | This single number decides 'any diabetes code ever recorded' vs 'only unresolved'. It's Decision D5. | You can state the fill rate as a percentage and say which cohort definition the data supports. | COUNT vs COUNT(column) null behaviour in SQL | Done | 0.0% resolved → D5 decided early, no active-as-of filter needed.
1.12 | 1 | Load every raw CSV into DuckDB as bronze_* tables, adding _loaded_at and _source_file. No typing, no dedupe, no validation. | Bronze is a faithful copy of what arrived. Cleaning here would destroy your ability to show what the raw data looked like. | Each bronze table's row count equals its CSV line count minus the header. | DuckDB read_csv_auto, CREATE TABLE AS SELECT, all_varchar, current_timestamp | Done | load_bronze.py, all_varchar=true, verified V1.5/V1.6/V1.7 on every run.
1.13 | 1 | Commit Day 1. | End every day with a commit. | git log shows a Day 1 commit with a real message. | — | Done
2.1 | 2 | Re-read the Principles section of DATA_QUALITY_SPEC.md, then plan corrupt.py on paper: which table, which rows, how many. | Injection is the one place you're deliberately writing bad data. Planning it stops you from corrupting rows you can't find again. | You have a written plan naming table, defect, and row count for all six. | — | Done
2.2 | 2 | Decide how many rows to corrupt per defect type. Record in Decisions. | Too few and the Pipeline page looks empty. Too many and Gold has no patients left to report on. | A number per defect, and a sanity check that Gold will still have a usable cohort afterwards. | — | Done | D3 recorded: 40/150/20/8/25/6 = 249 rows, all under 1% of table.
2.3 | 2 | Inject D1 — duplicate encounter rows (interface replay). | The most common real-world defect of the six. An HL7 interface re-posts a message and you get the encounter twice. | Known duplicate pairs exist in bronze_encounters and their ids are logged. | HL7 interface replay, idempotency in message processing | Done
2.4 | 2 | Inject D2 — null patient_id in observations. | A lab result that arrives without a resolvable patient. In production it's a failed foreign key on ingest. | Orphan observation rows exist and their source ids are logged. | referential integrity, orphan records | Done
2.5 | 2 | Inject D3 — an A1c value of 250 (mg/dL entered into a % field). | The classic unit error. It's the defect where quarantining is the wrong answer — this one you remediate. | Out-of-range A1c rows exist and are logged. | unit conversion errors in clinical data, mg/dL vs percent A1c | Done
2.6 | 2 | Inject D4 — a birth date in the future. | Registration typo. Trivial to catch, which is exactly why it belongs — not every check has to be clever. | Future-dated patient rows exist and are logged. | date sanity checks | Done
2.7 | 2 | Inject D5 — discharge timestamp before admission. | Timezone or clock drift between systems. Common enough that real warehouses check for it. | Chronologically impossible encounters exist and are logged. | timezone handling in clinical timestamps | Done
2.8 | 2 | Inject D6 — the same person registered under two different MRNs. | The most dangerous defect of the six, and the reason DQ6 routes to a human instead of merging. | At least one true duplicate-identity pair exists, sharing name and birth date, with different MRNs. | patient identity matching, master patient index, deterministic vs probabilistic matching | Done
2.9 | 2 | Write injected_defects.json — one entry per corrupted row: defect id, table, source row id, what you changed. | Without this file, catch rate is a claim. With it, it's a measurement. This file is the difference. | Entry count equals the number of rows you actually corrupted, and every entry has a resolvable row id. | JSON schema design, why ground truth matters in evaluation | Done | data/injected_defects.json - 249 entries, no timestamps so V2.3 can diff it. Committed.
2.10 | 2 | Make corrupt.py re-runnable from a clean Bronze without stacking corruption. | You will run this many times over the next five days. If it isn't idempotent you'll poison your own data and lose an hour. | Running it twice from clean Bronze produces the same injected_defects.json. | idempotency, deterministic seeding with random.seed | Done | Reload-first: corrupt.py calls load_bronze before injecting. V2.3 + V2.4 pass; JSON byte-identical across runs.
2.11 | 2 | Commit Day 2. | End every day with a commit. | Day 2 commit exists. | — | Done
3.1 | 3 | Create the three output tables with the exact schemas in DATA_QUALITY_SPEC.md: quarantine, identity_review, remediation_log. | Build the destinations before the checks, so no check has an excuse to drop a row silently. | All three tables exist with every column the spec names. | DDL, choosing column types | Done
3.2 | 3 | DQ1 — encounter uniqueness. Quarantine duplicates, keep the earliest. | 'Keep earliest' is a rule you chose. Be ready to say why earliest and not latest. | Duplicates from D1 are in quarantine with check_id DQ1, and one row per encounter survives. | window functions, ROW_NUMBER() OVER PARTITION BY, QUALIFY in DuckDB | Done
3.3 | 3 | DQ2 — referential integrity: every observation's patient_id exists in patients. | An observation with no patient can never reach a care team. Silently dropping it means nobody ever learns it arrived. | D2's orphans are in quarantine with check_id DQ2. | anti-join, LEFT JOIN WHERE NULL, NOT EXISTS | Done
3.4 | 3 | DQ3 — A1c plausibility (3.0-20.0). Remediate probable unit errors, quarantine the rest. Write the remediation rule down first. | This is the only check with two possible outcomes. The rule you write is the interesting part — 'divisible pattern suggests unit error' is a hint, not a rule. | The 250 is either corrected with an entry in remediation_log (original value preserved) or quarantined, and you can explain which and why. | unit conversion A1c, eAG vs A1c, defensive data correction | Done | D4: remediate via eAG. Range floor revised to 2.0. See validate.py dq3.
3.5 | 3 | DQ4 — birth date sanity: in the past, and implied age <= 120. | Simple, but state your 'today'. A hardcoded date rots; a run-time date makes results non-reproducible. Pick one and know why. | D4's rows are in quarantine with check_id DQ4. | date arithmetic in DuckDB, age calculation | Done | D7: ASOF = 2026-08-23, constant in validate.py.
3.6 | 3 | DQ5 — encounter chronology: discharge >= admission. | Watch the nulls. An open encounter with no discharge is valid, not a failure. | D5's rows are quarantined and open encounters are NOT. | three-valued logic in SQL, NULL comparison behaviour | Done
3.7 | 3 | DQ6 — identity: no two patients share name + birth date. Route matches to identity_review with status 'pending'. | Nothing downstream may merge these. A wrong merge combines two people's medication lists — that's a patient safety event, not a data bug. | D6's pair is in identity_review as pending, and both patient records still exist independently in Silver. | master patient index, match confidence scoring, human-in-the-loop review | Done
3.8 | 3 | Build the silver_* tables: surviving rows only, with real types cast (dates as dates, values as doubles). | Silver is where the data becomes trustworthy AND typed. Bronze was all strings on purpose. | Silver tables exist with correct types and a _dq_status column. | CAST vs TRY_CAST, why TRY_CAST matters on dirty data | Done | Added value_text to silver_observations: 315,450 text results would otherwise be nulled by TRY_CAST.
3.9 | 3 | Compute catch rate: read injected_defects.json, compare to quarantine + identity_review + remediation_log. Fill the DQ Matrix sheet. | The headline metric of the whole project. Report it honestly — a known, explained gap reads better than a claimed perfect score. | DQ Matrix shows detected counts per defect and the catch rate calculates. | precision and recall, evaluating against ground truth | Done | 6 of 6 types, 249 of 249 rows. Written to data/dq_report.json.
3.10 | 3 | ASSERT no silent drops: for every table, bronze rows = silver rows + quarantined rows. Make it fail loudly if not. | This is FR2 turned into a test. It's the assertion that proves your first principle rather than asserting it. | The check runs as part of the pipeline and raises if the arithmetic doesn't balance. | assertions in data pipelines, reconciliation counts | Done | reconcile() in validate.py raises SystemExit if any table fails to balance.
3.11 | 3 | Commit Day 3. | End every day with a commit. | Day 3 commit exists. | — | Done
4.1 | 4 | LOCK both cohort definitions in writing: 'diabetic patient' and 'open A1c gap'. Fill the blanks in DATA_DICTIONARY.md. | The docs call these the most interview-relevant lines in the repo. You now have the profiling data to answer them properly. Blocking — nothing else on Day 4 starts first. | Both blanks are filled with a definition AND a one-line justification referencing what you found on Day 1. | HEDIS comprehensive diabetes care specification, denominator vs numerator in quality measures | Done | D5 gained 'alive on as-of': 45 of 161 are deceased. Denominator 116. D6 as written.
4.2 | 4 | Build gold care_gap_a1c with every column the data dictionary lists. | One row per diabetic patient. This table is the product of the entire pipeline. | Table exists, one row per patient in the cohort, no duplicates. | CTEs, LEFT JOIN to preserve the never-tested | Done
4.3 | 4 | Handle the never-tested patient. days_since_a1c must be null-safe and gap_flag must be TRUE for them. | A patient who has never had an A1c is the highest-risk person on the list. A naive inner join silently deletes exactly the people you most need to find. | Patients with zero A1c results appear in Gold with a null last_a1c_date and gap_flag = true. | LEFT JOIN vs INNER JOIN, COALESCE, null propagation in arithmetic | Done | Inner-join demo in day4_gold.ipynb: 116 -> 95 rows, all 21 never-tested vanish = 84% of the gaps.
4.4 | 4 | Hand-verify three patients end to end against the raw CSVs: one with a recent A1c, one overdue, one never tested. | There is no unit test that substitutes for this. It's also the story you tell when asked 'how did you know it was right?' | Three patient ids traced from raw CSV to Gold row, and the numbers agree. | manual reconciliation, spot-checking | Done | Three patients traced raw CSV -> Gold in the notebook (recent / stale / never). All agree.
4.5 | 4 | Wire the whole thing to a single command: generate, load, corrupt, check, build gold. | FR1. Also the command that goes in the README's 'Run it' block. | One command on a clean checkout produces a populated Gold table. | Makefile, shell script orchestration, argparse | Done | pipeline/run_all.py [--generate] [--fresh]. V4.10: 12 s from nothing, same numbers.
4.6 | 4 | Record the headline numbers in Metrics: bronze / silver / quarantined / gold counts, cohort size, gap count. | These fill the README table and the P1 headline. Measure once, reuse everywhere. | Metrics sheet is fully populated. | — | Done
4.7 | 4 | Commit Day 4. | End every day with a commit. | Day 4 commit exists. | — | Done
5.1 | 5 | Scaffold the Next.js app in web/. | Four pages, no auth. Keep it plain — the content is the point, not the framework. | Dev server runs and serves a default page. | create-next-app, App Router vs Pages Router | Done
5.2 | 5 | Decide how the web app gets data: query DuckDB at request time, or export Gold to JSON at build time. Record the trade-off in Decisions. | This decision determines whether you can deploy to a static host. Deciding it now avoids rewriting on Day 7. | Decision recorded with its reasoning, and a spike proving the chosen route works. | serverless filesystem limits, static export, DuckDB in Node vs Python | Done | D9: static export. JSON for the pages, Parquet for DuckDB-WASM on P4.
5.3 | 5 | Build the synthetic-data banner as one shared component and put it on every page. | FR7. One component so it can't drift or get forgotten on a page. | All four pages render it, including error states. | shared layout components | Done
5.4 | 5 | P1 Overview: headline gap number, one-sentence description, architecture diagram, links to the other three pages. | A viewer with no context must understand the pipeline in under 3 minutes (G1). This page carries most of that. | The headline number is read from Gold, not typed in by hand. | — | Done
5.5 | 5 | P2: Bronze / Silver / Gold layer counts and the six checks with pass/fail and counts. | The data quality work has to be visible, not implied (G2). | Counts match what the pipeline actually produced. | — | Done
5.6 | 5 | P2: the quarantine table — every rejected row with its failure_reason. | This is the page that proves 'nothing is silently dropped'. Showing the rejects is the whole argument. | Every quarantined row is visible and its reason is readable in plain language. | — | Done
5.7 | 5 | P2: the identity review queue — duplicate MRNs awaiting a human decision. | Shows you understood that some problems are deliberately not automated. | The pending pair is shown with its match fields and confidence. | — | Done
5.8 | 5 | P2: one before/after example of a remediated record. | Concrete beats abstract. One visible correction explains remediation faster than a paragraph. | Original value and corrected value are both shown, with the rule that changed it. | — | Done
5.9 | 5 | P2: display the catch rate, including which defect (if any) got through and why. | An explained gap is more credible than a perfect score. | The number on the page matches the DQ Matrix sheet. | — | Done
5.10 | 5 | Deploy. Get a public URL today, not on Day 7. | Deployment always surprises you. Finding out on Day 5 costs an hour; finding out on Day 7 costs the project. | A public URL loads P1 and P2 with real data. | Vercel deploy, environment variables, build vs runtime data | Done | GitHub Pages (Vercel needs an interactive login). Live since Day 5.
6.1 | 6 | Rewrite the role matrix in ACCESS_CONTROL.md from your own floor experience as a PCT. | The doc says your version is more credible than the starting one. This is the part of the project only you can write. | The matrix reflects real unit practice and the README says so. | minimum necessary standard, role-based access control | In progress | Implemented from ACCESS_CONTROL.md starting matrix - still needs Franklin's revision from floor experience.
6.2 | 6 | Implement role filtering in the query layer — server-side. Restricted fields must never reach the browser. | A reviewer will open dev tools. If A1c values are in the payload for a PCT, the demo argues against its own thesis. | Network payload for the PCT role contains no restricted fields at all. | server-side vs client-side authorization, why hiding columns in CSS is not security | Done | Static site has no request-time server, so filtering is build-time SQL: one payload per role, restricted columns never SELECTed.
6.3 | 6 | Apply row-level filtering too, not just columns: a PCT sees only patients on their assigned unit. | FR4 says both. Column-only filtering is the shortcut people take, and it's the one that gets noticed. | Switching to PCT changes the number of rows AND the number of columns. | row-level security, predicate pushdown | Done | Unit = care setting of most recent encounter (Synthea has no rostering). 70 / 106 / 116 rows.
6.4 | 6 | Show 'Not available for this role' placeholders instead of silently omitting restricted columns. | The restriction being visible is the entire point. A missing column teaches the viewer nothing. | Restricted columns are present and labelled, with no data behind them. | — | Done
6.5 | 6 | Build the gap-count-by-age-band chart. Decide the banding first (Decisions sheet). | 10-year bands are conventional; clinical bands are defensible if you can name the reasoning. Either is fine — having a reason is not optional. | Chart renders from Gold and the bands are documented. | age banding in population health, HEDIS age stratification | Done
6.6 | 6 | TEST YOUR OWN CLAIM: select PCT, open dev tools, inspect the network response. Confirm no restricted data is present. | You are checking the thing a skeptical reviewer will check first. Do it before they do. | Screenshot or note confirming the payload is clean. If it isn't, 6.2 is not done. | browser devtools network tab | Done | V6.1 passes: no restricted substring appears anywhere in care_gap_pct.json.
6.7 | 6 | Commit Day 6. | End every day with a commit. | Day 6 commit exists. | — | Done
7.1 | 7 | Write the ten preset question chips. | Chips are the demo path. Someone with 30 seconds clicks a chip — make those ten answers your best ones. | Ten chips, all returning correct answers from Gold. | — | Done
7.2 | 7 | Implement natural language to SQL over the gold tables only. | Scoping it to Gold keeps the schema small enough for the model to get right, and keeps quarantined data out of answers. | A free-text question returns a correct answer from Gold. | text-to-SQL prompting, passing schema as context, Claude API tool use | Done
7.3 | 7 | Display the generated SQL above every single answer. | Non-negotiable per the PRD. Showing the query is what makes the answer auditable instead of magic. | SQL is visible for chip answers and free-text answers alike. | — | Done
7.4 | 7 | Enforce SELECT-only. Reject anything that is not a single SELECT statement. | FR5. Assume the input is hostile — a reviewer WILL try to drop a table. | Attempts at DROP, DELETE, UPDATE, INSERT and stacked statements are all refused. | SQL injection, allowlist vs blocklist validation, parsing vs regex, read-only connections | Done | Allowlist on the statement's actual verb. A test found WITH x AS (SELECT 1) DELETE FROM patients passing - now walks the CTE list. 19/19 cases.
7.5 | 7 | Adversarially test with five deliberately bad questions. Each must return one clean human sentence. | Explicit success criterion in the PRD. Try: an out-of-scope clinical question, a request for a field no role can see, a destructive statement, gibberish, and a question about data that isn't in Gold. | Five bad inputs, five plain sentences, zero stack traces (FR6). | graceful degradation, error message design | Done | Free-text refuses anything unmatched with one sentence naming what it can answer.
7.6 | 7 | Add the audit log — role, question, generated_sql, row_count, run_at — and surface it on P2. | Access logging is a real requirement in clinical systems and costs you almost nothing to show. | Every query appends a row, and the log is visible on the Pipeline page. | audit logging, HIPAA audit controls | Done | Audit log on P4: role, question, SQL, rows, outcome. Refusals logged too.
7.7 | 7 | Error sweep: click through every page trying to break it. No stack trace may be reachable. | G4 and FR6. One raw exception on a portfolio site undoes a lot of careful work. | You tried to break all four pages and got human sentences every time. | error boundaries, Next.js error handling | Done
7.8 | 7 | Fill every blank in README_TEMPLATE.md from the Metrics and DQ Matrix sheets. | The README is what most people read instead of the app. Blanks left in look abandoned. | No underscores remain in the README. | — | Done
7.9 | 7 | Write 'What I'd do differently at scale' in both the README and DATA_QUALITY_SPEC.md. | This section is where a senior reviewer decides how you think. Name real tools and real trade-offs. | Both sections written, naming specific approaches rather than generalities. | Great Expectations, dbt tests, partitioning by load date, drift alerting | Done | Written from this week's real friction: DuckDB single-writer, the four-flag reproducibility failure, quarantine as a dead-letter queue.
7.10 | 7 | Final deploy, then record the 90-second Loom. | Script it: the question, the dirty data, the catch rate, the role switch. Ninety seconds is short — rehearse once. | Public URL is current and the Loom link is in the README. | — | Not started
7.11 | 7 | Show it to a non-technical person. Can they explain what it does after 3 minutes? | The last success criterion, and the only one you can't self-assess. | They can explain it back to you without using the word 'pipeline'. | — | Not started

## Decisions
Decisions log
Every judgment call the docs left open. The 'Rationale' column is what you'll actually be asked about — write it as if someone will read it aloud back to you.
ID | Decision to make | Options / considerations | Why it matters | Decide by | Your call | Rationale (one or two sentences)
D1 | Synthea population size | 1,000 keeps every query instant. 5,000+ makes row counts look more credible but slows every iteration all week. | Affects iteration speed for seven days, and how impressive the Pipeline page numbers look. | Day 1 | 1,000 (-p 1000) → 1,153 patient records | Synthea -p counts survivors, so 1,000 alive + 153 deceased. Keeps every query sub-second while still yielding a 161-patient cohort. Deceased are loaded but excluded from the gap denominator on Day 4.
D2 | Synthea state and random seed | Any state; the seed is the important half. | A fixed seed is what makes your README numbers reproducible by a reviewer. Without one, nobody can verify anything you claim. | Day 1 | Massachusetts; -s 20260823 -cs 20260823 -r 20260823 -e 20260823 | V1.3 FAILED on the Day 1 command (-s only): four weeks later the same seed gave 1,151 patients, not 1,142. -s pins the patient RNG but the clinician seed (-cs), reference date (-r) and end date (-e) all default to the wall clock. Each was found by fixing one and seeing what still moved. With all four, two runs are identical in content. Data regenerated 2026-09-20; every number here is from the pinned output. See DAY_1_DECISIONS.md D2.
D3 | How many rows to corrupt per defect type | Enough to be visible on P2; few enough that Gold still has a real cohort. | Too few looks contrived on the page. Too many empties the care-gap list you're supposed to be producing. | Day 2 | D1 40 · D2 150 · D3 20 · D4 8 · D5 25 · D6 6 (≈249 rows) | Nothing exceeds 1% of its table (largest is D4 at 0.7% of patients). Enough that quarantine reads as a real work queue on P2, small enough that the 161-patient cohort and its 133 A1c-tested patients survive (V2.7). D3 rows are sampled from cohort patients so Decision D4 (remediate vs quarantine) visibly moves the gap count on Day 4.
D4 | DQ3 remediation rule for the A1c unit error | Correct it by a conversion rule, or quarantine it. The spec hints at 'divisible pattern' but does not define the rule. | This is the only check with two possible outcomes. The rule you write is the most technically interesting decision on Day 3. | Day 3 | Remediate via eAG when 20 < value ≤ 600 (rule A1C_MGDL_TO_PCT_EAG); quarantine everything else out of range | A1c of 250 is impossible as a percent but ordinary as mg/dL glucose. Converted with the ADA eAG mapping A1c = (v + 46.7) / 28.7 → 10.3 %, original kept in remediation_log, Silver row flagged 'remediated' so the correction is reversible in one WHERE clause. Quarantine was the alternative; on this extract both give 69 open gaps, so decided on principle: a logged, reversible correction beats throwing the row away for everyone. Would want clinician sign-off before running on real data.
D5 | Cohort definition — 'diabetic patient' | Any diabetes SNOMED code ever recorded, or only conditions with no resolved_date? Day 1 task 1.11 gives you the fill rate that decides it. | Named in the docs as one of the two most interview-relevant lines in the repo. Changes your denominator, and therefore every number on P1. | Day 4 | Any of 8 diabetes SNOMED codes ever recorded AND alive on the as-of date. Denominator = 116. | Decided Day 1 — the evidence arrived early. Anchoring on 44054006 alone misses 73 patients who carry a diabetic complication with no underlying dx code (45% of cohort, and the sickest half). Prediabetes 714628002 excluded: 439 patients, would triple the denominator. 0 of 835 diabetes rows have a stop date, so "ever recorded" needs no date logic. See pipeline/cohort.py. Day 4 added the alive clause: 45 of the 161 code-carriers died before 2026-08-23, and a care-gap list is a call list - HEDIS excludes deceased members too.
D6 | Cohort definition — 'open A1c gap' | No result in 365 days. But: does an ordered-but-not-resulted test count as a gap? What about a result from a different lab system? | The other of the two. It is also the honest one — 'ordered but no result' is a real operational distinction that most demos ignore. | Day 4 | No A1c result (4548-4, numeric, on/before as-of) in the 365 days before as-of. Never tested = gap. >365 is a gap, 365 is not. | Ordered-but-not-resulted is not observable in Synthea (no orders table, 0 procedure rows mention A1c), so v1 counts it the same as never ordered and says so. Results in other lab systems are likewise invisible: the number is 'no result we can see'. Remediated 250s count as results (D4). Result: 25 of 116 (21.6%), 21 of them never tested - the 21 an inner join would have silently deleted.
D7 | What counts as 'today' for age and gap math | Run-time current date, or a fixed as-of date stored with the run. | A run-time date makes your README numbers drift every day. A fixed date is reproducible but goes stale. Both are defensible; pick knowingly. | Day 4 | Fixed as-of date 2026-08-23 (the Synthea end date), constant ASOF in validate.py | The data stops on 2026-08-23; no patient ever gets another A1c. A wall-clock 'today' pushes more patients past the 12-month line every day for no reason (69 gaps on the as-of date, higher every day after). Freezing today makes the report describe the data, not the calendar. Same lesson as V1.3, one layer up.
D8 | Do quarantined rows ever re-enter the pipeline after remediation? | Open question in the PRD. Reprocessable quarantine is the production answer; a one-way table is the honest v1 answer. | Says whether quarantine is a dead-letter queue or a work queue. Good answer either way if you can name the trade-off. | Day 4 | No. Quarantine is a dead-letter queue in v1; the replay path is named as scale work. | Reprocessing needs three things this project does not have: a replay path, a resolved_at column, and a rule for whether a replayed row enters Silver under its original load date or today's. Building a half version would make the reconciliation assertion ambiguous, which is the one guarantee worth keeping exact. Written up in DATA_QUALITY_SPEC.md under what I would do differently at scale.
D9 | How the web app reads the data | Query DuckDB at request time, or export Gold to static JSON at build time. | Determines where you can deploy and whether P4's SQL is live. Decide before you build P2, not after. | Day 5 | Static export at build time. JSON for the pages, Parquet for DuckDB-WASM. | Decided Day 5, recorded here late. A server runtime holding clinical.duckdb would have failed on a serverless filesystem, and the deploy had to work on Day 5 rather than Day 7. Exporting both formats costs 458 KB: the pages render from JSON with no engine to load, and P4 queries the Parquet in the browser so the SQL it shows is the SQL that ran. The trade-off accepted is that the site reads a snapshot - re-running the pipeline without re-exporting leaves it stale, which is why export_web is the last stage of run_all.py.
D10 | Default role on page load | PRD recommends PCT. | PCT first means the viewer sees the most restricted view before the fullest one, which makes the role switch land harder. | Day 6 | PCT — the most restricted view loads first | The first thing a viewer sees should be a restriction, not a full table. Opening on PCT means the 12 'not available' cells are visible before anything else, which is what the page is arguing.
D11 | Age banding for the chart | 10-year bands, or clinical bands (e.g. HEDIS diabetes stratification). | Small choice, but 'because HEDIS stratifies that way' is a much better answer than 'it looked nice'. | Day 6 | HEDIS bands: 18-44, 45-64, 65-75, 76+ | Not round decades. The HEDIS diabetes measure applies to members 18-75 and stratifies 18-64 and 65-75, so three of the four boundaries are the measure's own. The 76+ band sits outside the measure's age range entirely - 21 of 116 patients - which is worth showing rather than hiding. Bands cover every patient (V6.8) and their gaps sum to 25 (V6.7).
D12 | Which model / API powers P4's text-to-SQL | Provider, model, and whether the schema goes in the prompt. | Affects cost, latency on a live demo, and what you say when asked how you kept it from hallucinating table names. | Day 7 | No model. Ten preset questions with hand-written SQL, run in DuckDB-WASM in the browser. | D9 made the site a static export, so there is nowhere to hold an API key - a key shipped to the browser is a public key. The plan allows this cut ('ten working chips and no free-text box still demonstrates the idea') and it buys something a hosted model would not: the SQL displayed is literally the SQL executed, against the same Parquet the site ships, so a reviewer can copy it and get the same rows. The free-text box matches wording to the presets and refuses everything else by naming what it can answer. The page says it is a query builder, not a language model.
D13 | Which lab defines the care gap — A1c or blood glucose | Glucose is the larger table (10,439 vs 8,941) and covers more of the cohort. Both are reasons to reject it. | Choosing glucose would silently break the claim that this implements a real published measure. | Day 1 | HbA1c, LOINC 4548-4. Glucose (2339-0, 2345-7) is context only, never a gap definition. | A1c integrates ~3 months of blood sugar; glucose is a snapshot. In our own data the within-patient, within-year spread is 6.7% of the mean for A1c vs 21.3% for glucose. Glucose is also drawn on everyone incidentally — 159 of 161 cohort patients have one vs 133 with an A1c — so its absence carries no signal. And HEDIS specifies A1c; no measure anywhere requires an annual glucose.
D14 | Synthea export format — CSV or FHIR | FHIR JSON is more realistic interchange; CSV loads in one line of DuckDB. | Determines how much of the seven days is spent parsing versus on the actual subject. | Day 1 | CSV (--exporter.csv.export true, all three FHIR exporters false) | FHIR conformance is an explicit PRD non-goal. The subject of this project is data quality, not nested resource parsing. CSV spends the time on the subject.
D15 | Which of the 18 Synthea CSVs get loaded into Bronze | All 18 (773 MB), or the five the care gap actually needs. | claims_transactions alone is 1,094,500 rows — 40% of total volume with no clinical role. | Day 1 | Five: patients, encounters, conditions, observations, medications. | Everything else is billing (claims, payers), or clinical data with no bearing on an A1c gap (imaging_studies, procedures, devices, supplies, allergies, careplans, immunizations). organizations/providers may be added on Day 6 if role views need facility names.

## DQ Matrix
Injected defects vs. checks — catch rate
Fill the amber columns on Day 3. The catch rate calculates itself. If it is below 100%, say which defect got through and why — an explained gap beats a claimed perfect score.
Defect | What it is | Table | Realistic cause | Check that should catch it | Rows injected | Rows detected | Type caught? | Notes / why it escaped
D1 | Duplicate encounter rows | encounters | Interface replay / double post | DQ1 — encounter uniqueness | 40 | 40 |  | Caught by its own check, all rows
D2 | Null patient_id | observations | Failed foreign key on ingest | DQ2 — referential integrity | 150 | 150 |  | Caught by its own check, all rows
D3 | A1c value of 250 | observations | Unit error: mg/dL in a % field | DQ3 — A1c plausibility | 20 | 20 |  | Caught by its own check, all rows
D4 | Birth date in the future | patients | Registration typo | DQ4 — birth date sanity | 8 | 8 |  | Caught by its own check, all rows
D5 | Discharge before admission | encounters | Timezone or clock error | DQ5 — encounter chronology | 25 | 25 |  | Caught by its own check, all rows
D6 | Same patient, two MRNs | patients | Registered twice at different sites | DQ6 — patient identity | 6 | 6 |  | Caught by its own check, all rows
Catch rate
| Defect types detected |  | This is the number the README and the Pipeline page quote.
| Catch rate (by type) |  | Percent for the headline.
| Catch rate (by row) |  | Stricter measure. Detecting one duplicate of eight is not the same as catching the defect class.
Rows injected (total)
Rows detected (total)
Reminder: 'detected' means the row landed in quarantine, identity_review, or remediation_log with the right check_id — not that you saw it in a printout.

## Metrics
Metrics to collect
Measure once, reuse everywhere. Every one of these fills a specific blank in README_TEMPLATE.md or a number on a page.
# | Metric | Your number | Where it goes | When you measure it
1 | Bronze rows — patients | 1153 | README architecture table, P2 layer counts | Day 1
2 | Bronze rows — encounters | 67755 | README architecture table, P2 layer counts | Day 1
3 | Bronze rows — conditions | 40811 | README architecture table, P2 layer counts | Day 1
4 | Bronze rows — observations | 870510 | README architecture table, P2 layer counts | Day 1
5 | Bronze rows — medications | 59273 | README architecture table, P2 layer counts | Day 1
6 | Distinct diabetes SNOMED codes found | 8 in cohort (9 matched "%diabet%"; prediabetes 714628002 excluded) | DATA_DICTIONARY.md code table | Day 1
7 | A1c LOINC code confirmed | 4548-4 — Hemoglobin A1c/Hemoglobin.total in Blood, units "%" | DATA_DICTIONARY.md code table | Day 1
8 | A1c value range (min / median / max) | 2.3 / 4.1 / 8.8 (n=8,941; 951 below DQ3 floor of 3.0 → revise floor to 2.0) | Sanity check for DQ3's 3.0-20.0 bounds | Day 1
9 | % of diabetes conditions with a resolved_date | 0.0% (0 of 835 diabetes condition rows have a STOP date) | Decides cohort definition D5 | Day 1
10 | Rows corrupted (total) | 249 | P2 pipeline page | Day 2
11 | Silver rows (total, all tables) | 1039325 | README architecture table | Day 3
12 | Quarantined rows (total) | 223 | README architecture table, P2 | Day 3
13 | Rows in identity_review | 6 | P2 identity queue | Day 3
14 | Rows in remediation_log | 20 | P2 before/after example | Day 3
15 | Catch rate | 6 of 6 types, 249 of 249 rows | README headline, P2 headline | Day 3
16 | Diabetic patients in cohort (denominator) | 116 | README result line, P1 headline | Day 4
17 | Patients with an open A1c gap (numerator) | 25 | README result line, P1 headline | Day 4
18 | Gap rate % | 21.6% | P1 headline | Day 4
19 | Patients never tested for A1c | 21 | P3 — the highest-risk subgroup | Day 1
20 | End-to-end pipeline runtime | 13 s warehouse-to-Gold; ~4 min with --generate (Synthea + jar download) | Nice to quote when asked about scale | Day 4

## Learning Log
Learning log
Rate yourself 1-5 on saying the answer out loud, unprompted, with no notes. Anything 3 or below is a hole to close before you send this link to anyone.
# | Concept | The question you should be able to answer cold | Day it comes up | Confidence 1-5 | Your answer, in one or two sentences
1 | Medallion architecture | Why three layers? What specifically belongs in Bronze that must NOT be cleaned there? | 1
2 | Synthetic data and its limits | What can't you claim about a model or a pipeline validated only on Synthea data? | 1 |  | Nothing about real-world performance: Synthea has no typos, no interface replays, no duplicate registrations, and names carry numeric suffixes so identity matching is trivially clean. The defects are the ones I injected, so catch rate measures my checks against my own defect list, not against reality. Also learned: synthetic does not mean deterministic - the generator has a 'now' that follows the wall clock unless pinned (see #13).
3 | Clinical code systems | When do you use SNOMED vs LOINC vs RxNorm, and why do you join on codes rather than display names? | 1
4 | HEDIS / quality measures | What is the denominator and numerator of a comprehensive diabetes care A1c measure? | 1, 4
5 | Ground truth and evaluation | Why inject defects and log them, rather than just running checks and reporting what you found? | 2
6 | Idempotency | Why does corrupt.py have to be re-runnable, and what breaks if it isn't? | 2
7 | Quarantine over dropping | Someone asks why a patient is missing from the care-gap report. Walk them through how you'd answer. | 3
8 | Referential integrity | What is an orphan record, and why is deleting one worse than keeping it aside? | 3
9 | Patient identity resolution | Why does DQ6 route to a human instead of merging? What is the specific harm of a wrong merge? | 3
10 | Remediation vs. overwriting | Why keep original_value? Who ever needs it? | 3
11 | Null handling in SQL | How does a naive inner join silently delete the highest-risk patients from your report? | 3, 4
12 | Cohort definition | Defend your definition of 'diabetic patient'. What would change if you'd chosen the other one? | 4
13 | Reproducibility | A reviewer clones your repo and runs it. Do they get your README's numbers? What guarantees that? | 1, 4 |  | Only if every source of randomness AND every source of time is pinned. I tested it: -s alone failed four weeks later (1,151 patients, not 1,142) because Synthea's clinician seed, reference date and end date all default to the wall clock. Now -s -cs -r -e are all fixed and two runs match in content. 'Reproducible' means same content, not same bytes - the export is multi-threaded so row order varies; verify with a sorted diff or DuckDB EXCEPT, never md5. The README numbers are guaranteed by the pinned command in D2 plus the Bronze row-count check, not by a claim.
14 | Minimum necessary standard | What is it, and why is this demo NOT HIPAA compliant? | 6
15 | Server-side authorization | Why is filtering columns in the browser not access control? | 6
16 | Row vs column level security | Give an example where column filtering alone still leaks information. | 6
17 | Audit logging | What do clinical systems log about data access, and why? | 6, 7
18 | SQL injection / SELECT-only | How do you enforce read-only? Why is an allowlist better than blocking dangerous keywords? | 7
19 | Text-to-SQL failure modes | How do you stop the model inventing a table that doesn't exist? What happens when it does anyway? | 7
20 | Honest error handling | Why does 'I can't answer that, but here's what I can answer' beat a stack trace or a wrong answer? | 7
21 | Scale trade-offs | Everything here runs on one machine. What breaks first at 10 million patients, and what would you change? | 7